WIOA Quarterly Monitoring Dashboard – PY25

Contractor: People Incorporated of Virginia
Reporting Period: 3rd Quarter Mid Quarter Report PY2025

I. Participant Enrollment & Demographics

| Category | Target for PY25 | Quarterly Actual (1/1-2/28) | Cumulative Total | Notes/Variance Explanation |
| --- | --- | --- | --- | --- |
| Adult Participants | 121 | 25 | 110 | On Target |
| Dislocated Worker (DLW) | 37 | 8 | 58 | Met Target |
| Youth Participants | 51 | 12 | 73 | Met Target |
| % Served in Each Jurisdiction* | Equitable Access | See Attachment | See Attachment |  |
| Individuals with Disabilities | 25% of the total | 2 | 31 (12.91%) | Behind on Target |
| Minority Participants | 40% of the total | 4 | 40 (16.66%) | Behind on Target |
| Out-of-School Youth | 75% of youth | 2 | 50 (83.33%) | On target |

*Attach a breakdown of participant counts by jurisdiction.

II. Participant Outcomes

Adult:

| Outcome Category | Goal | Quarterly Actual | Cumulative Total | Notes/Variance Explanation |
| --- | --- | --- | --- | --- |
| Credential Attainment | 78% | 64.86% (24 of 37) | 62.36% (56 of 87) | Below Target |
| Entered Unsubsidized Employment 2nd Q after Exit | 85% | 70.00% (10 of 13) | 88.57% (62 of 70) | On Target |
| Entered Unsubsidized Employment 4th Q after Exit | 86.5% | 80.85% (38 of 47) | 80.56% (87 of 108) | Below target |
| Measurable Skills Gain | 65% | 46.47% (33 of 71) | 46.47% (33 of 71) | Below Target |

Dislocated Worker:

| Credential Attainment | 79.47% | 33.33% (1 of 3) | 77.78% (7 of 9) | Slightly below target |
| --- | --- | --- | --- | --- |
| Entered Unsubsidized Employment 2nd Q after Exit | 82% | 66.67% (8 of 9) | 81.82% (18 of 22) | On target |
| Entered Unsubsidized Employment 4th Q after Exit | 87.8% | 90.00% (9 of 10) | 84.78% (39 of 46) | Slightly below target |
| Measurable Skills Gain | 65% | 57.14% (12 of 21) | 57.14% (12 of 21) | Below target |

Youth:

| Credential Attainment | 60% | 63.63% (21 of 27) | 78.46% (51 of 65) | On target |
| --- | --- | --- | --- | --- |
| Entered Unsubsidized Employment 2nd Q after Exit | 78.59% | 72.72% (9 of 9) | 79.63% (43 of 54) | On target |
| Entered Unsubsidized Employment 4th Q after Exit | 80% | 82.35% (28 of 34) | 78.57% (66 of 84) | Slightly below target |
| Measurable Skills Gain | 65% | 30.00% (12 of 40) | 30.00% (12 of 40) | Behind on Target |

II. Strategic Innovations & Access

| Area | Description of Activities This Quarter | Outcome/Impact |
| --- | --- | --- |
| Digital Engagement Tools (e.g., Metrix, Conover) | Conover, NorthStar | Youth increase their work-readiness, and all participants enhance their digital skills for employment. |
| Employer Partnerships / Work-Based Learning | Provided to Kimber in the quarterly business services report |  |
| Outreach Efforts | Outreach targeting Community College and public schools | People Inc. has been meeting with the community college workforce development departments – WCC, VHCC, and NRCC, and they have met with Adult Education. Additionally, People Inc. has been reaching out to curriculum/department heads regarding some of our in-demand occupations at community colleges and is beginning outreach/recruitment through public schools. |
| Cross-Partner Collaboration (e.g., referrals, co-enrollment) | Co-enrollment/partnerships | People Inc. has received an announcement that we will receive a SPARK Energy Grant – they will co-enroll WIOA youth with that grant once it is executed. |

IV. Concerns/Technical Assistance Needs

Submitted by Clay Stein: __ Clay Stein_____________________________________

Reviewed by (NRMR WDB Program Manager): ____________________________

Date of Review Meeting: ___________________